## Workshop Summary
Fit-to-Standard Workshop ¦ Outcome
Workshop ID | R2R-CO-36
Workshop Title | Overhead Projects
Workstream | Record-to-Report
Area | Controlling
Scope Item(s) | 1NT, 35F
Date | 2026-10-08
Workshop Lead | Armin Turken
Business Process Owner | Patric Dietermann
Countries / Entities | Global, Finland, China
Attendees | [List of attendees]
Absentees | [List of absentees]
Overall Result | Completed - Gaps Identified
Workshop Deck URL | Overhead Projects
Document Approval
Workstream Lead | Patric Dietermann
Approval Status | Draft
Approved By | [Name of approver]
Approval Date
Approval Comment | [Optional comment or reason for rejection / rework]
Approval Governance
• Document approval is valid only when Approval Status is set to Approved.
• Approved By and Approval Date must be completed.
• All material open decisions and actions must either be closed or transparently documented.
• The Customer Workstream Owner approves the complete workshop outcome document, not individual log entries.
• The SharePoint version and documented approval process serve as the authoritative approval record.

## Outcome Log
Fit-to-Standard Outcome Log
Outcome ID | Record Type | Process Step | Topic | Scope Item(s) | System Demo Result | Business Requirement | Fit Assessment | Gap Justification | Impact Category | Country / Entity | Criticality | Legal / Regulatory | Proposed Solution | Decision | Decision Status | Decision Owner | Action | Action Owner | Due Date | Action Status | Dependency | Requirement URL | Remarks
R2R-CO-33-001 | Requirement | Create Cost Center | Master Data | J54 | Creation and change of Cost Centers are similar to ECC. | Additional Cost Center Categories needed, Adaptation of default settings of Cost Center Categories | Fit with Configuration | Validate local exceptions. | Configuration | Global, Finland, China | Must | No | Create new Cost Center Categories and rename/adapt the existung one's. |  | Approved | R2R Owner | Validate local exceptions. | Local R2R Leads | 2026-10-16 | Open | Localization | [Paste requirement URL] | Mock data

## Dropdown Lists
Dropdown master data ¦ Extend the Excel tables below to add further values
Workstream | Workstream ID | Workstream | Area | Area ID | Record Type | Fit Assessment | Impact Category | Criticality | Legal / Regulatory | Decision Status | Action Status | Overall Result | Document Approval Status
Lead-to-Cash | L2C- | Record-to-Report | Finance | FI- | Requirement | Fit | Process | Must | Yes | Not Required | Not Required | Completed - Fit | Draft
Purchase-to-Pay | P2P- | Record-to-Report | Controlling | CO- | Assumption | Fit with Configuration | Configuration | Should | No | Decision Pending | Open | Completed - Gaps Identified | In Review
Plan-to-Fulfill | P2F- | Record-to-Report | Asset Accounting | AA- | Issue | Fit with Process Change | Master Data | Could | Not Assessed | Approved | In Progress | Follow-up Required | Approved
Special Order Process | SOP- | Record-to-Report | Treasury | TRM- | Information | Gap / Extension Required | Data Migration | Not Applicable |  | Rejected | Blocked | Decision Pending | Rejected
Service-to-Cash | S2C- | Record-to-Report | Group Reporting | GR- |  | Open / To Be Assessed | Integration |  |  |  | Closed |  | Rework Required
Issue-to-Solution | I2S- | Lead-to-Cash | Project-to-Cash | P2C- |  | Out of Scope | Forms / Output
Idea-to-Market | I2M- | Lead-to-Cash | Lead-to-Order | L2O- |  |  | Reporting / Analytics
Record-to-Report | R2R- | Lead-to-Cash | Order-to-Cash | O2C- |  |  | Roles & Authorizations
Analyze-to-Optimize | A2O- | Analyze-to-Optimize | Management Reporting | MR- |  |  | Workflow
Authorization | AUT- | Analyze-to-Optimize | Financial Planning | FP- |  |  | Extension
Master Data Management | MDM- | Plan-to-Fulfill | Demand-to-Supply | D2S- |  |  | Localization / Legal
Data Migration | DMG- | Plan-to-Fulfill | Ship-to-Customer | Sh2C- |  |  | Testing
Architecture & Interfaces | ARC- | Plan-to-Fulfill | Plan-to-Produce | PP- |  |  | Organizational Change
Organizational Change Management | OCM- | Plan-to-Fulfill | Warehouse Internal | WSI-
Integration | INT- | General | No Area
Salesforce | SF- | Salesforce | Sales | Sales-
ON EBX | EBX- | Salesforce | Service | Service-
|  | Integration | Solution Architecture | SolArch-
|  | Record-to-Report | General | GN-
|  | Idea-to-Market | Product Development | PD-
|  | Idea-to-Market | Product Compliance | PC-
|  | Issue-to-Solution | Quality Management | QM-